## README
Last Update | 2019-04-22
Author | Samuel Dominguez,
Email | sdomi003@ucr.edu,
Description | Parking at UCR TAPS web page, can show available spaces in parking lots. Parking space app can fetch available information from webpage, and can show in app and send notifications about preferred parking location depending on the class schedule.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Registration | As an unregistered customer who is insterested in the app, I want to register an account so that I can login the app | 3 | 1 |  | .
2 | Login/Logout | As a registered user, I want to login my account with user name and password, and logout my account to end the session | 1 | 1 |  | .
3 | Link UCR Schedule | As a user, I want to be able to upload a calendar file of my schedule. | 3 | 1 |  | .
4 | Home Screen | As a user, there should be an intuitive home screen that allows me to manually input a destination and get the closest available lot. | 5 | 2 |  | .
5 | See closest available parking to my building | As a user, I want to be able to know which parking lot is the closest to the building my class is going to be at in order to save time walking. | 3 | 1 |  | .
6 | Receive notifications | As a student commuter, I want to receive notifications when parking is available near my class time according to my schedule. | 3 | 2 |  | .
7 | Use Google Maps to route to parking | As a user, if certain campus roads leading to parking lots are congested, I would like to be taken on alternative routes through campus. | 5 | 2 |  | .
8 | Filter permitted parking lots based on permit level | As a student commuter, I want to be able to find the best possible parking option for my parking pass. | 2 | 3
9 | Report alternative transportation if it is faster or more convenient. Google api, check restrictions | As a user, I want to check the app or receive a notification before class on a more convenient transportation method (bus, walking, biking) if such a method exists. | 4 | 3
10 | Option to send notification whenever my favorite lot is getting full a few minutes before my class starts. | As a user, I want to be notified on alternative parking options when I am unable to park at my usual lot | 4 | 4
11
12
13
| Total |  | 33

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task1: Create User Interface - Thomas,Jessica
Task2: Registration and Login Database - Edmund
Task3: Personal Info Database - Edmund,Thomas,Jessica
Task4: Parking Algorithm -Samuel,Edmund
Task5: Google API - Edmund
Task6: Find Lot Information - Samuel
Task7: Recieve Notifications - Thomas
Task8: Google Maps - Samuel
Task9: Permit Levels
| Task10: Scheduling Database -Jessica | Task10: Scheduling Database - Edmund
Task11:Alternate Transportation Option - Samuel
Task12:Twitter Feed - Krishna
Task13: ParkMobile Redirect for passes - Jessica
Task14: User Preferences (build upon Personal Info Database) - Edmund
Task15: Scrubbing and Optimization

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | David Hoffman | Task 1: Login Page Design (John Li)
1 | David Hoffman | Task ?
.. | .. | ..

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 2 | 2 | 33 | 30.625
2 | 36 | 3 | 5 | 31 | 26.25
3 | 36 | 3 | 8 | 28 | 21.875
4 | 36 | 4 | 12 | 24 | 17.5
5 | 34 | 3 | 15 | 19 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0